## estimate
Task Detail | Description | Service | Man Days
DB/System Setup | DB/System Setup
DataBase and Application Setup | Need to create database schema and application structure. | Software Development | 1
Admin | Admin Functionality
Login | Login contains one type of user : 1) Admin. | Software Development | 0.5
Forgot Password. (API) | If a user(Admin) forget the password, they will be able to recover the password by submitting and forget password request to admin. | Software Development | 0.875
Manage Employees | Admin will be able to add, update, and delete employees from the web backend. Following information of the user will be entered by the admin - 1. Name 2. Role 3. Email ID 4. Phone Number | Software Development | 1.5
Manage Role | Admin can add/update/delete from system | Software Development | 0.75
Manage Products | Admin will be able to add, update and delete the products and manage details such as name, SKU, category, barcode, unit of measurement, cost, taxes, and discount. Furthermore, admin will assign a printer to each of the product. | Software Development | 2.5
| Admin will be able to manage inventory (stock levels) and will be able to monitor the decreasing levels as per the received orders | Software Development | 0.5
Manage Profile | Admin will manage (add/ edit/ delete) retail outlet details like Store Name, Address, Area, Postal code, and logo. | Software Development | 1.5
Manage Category | Admin will be able to add/edit/delete categories for their products. Category name will be saved. | Software Development | 0.75
Manage Taxes | Admin will be able to add/edit/delete tax details such as name, and percentage. | Software Development | 0.75
Manage Customers | Admin will be able to add/edit/delete customers added by the employees from the application. | Software Development | 0.625
Manage Offers | Admin will be able to add/edit/delete offers against each product. Admin will be able to add offers like “Buy one Get one Free” by entering details like “Original Product Name, Free Product Name, Original Product Quantity and Free Product Quantity”. Offers will have publish date and expiry date. | Software Development | 2.5
Manage Discount | Admin will be able to add/edit/delete discount against each product. To add discount the admin will be able to enter the “Discount Percent or Discount Amount” in the provided field. Discounts will have publish date and expiry date. | Software Development | 1.2
Reports | Admin will be able to generate sales reports by following: 1. By Item 2. By Category 3. By Users 4. By Payment Type 5. Sales during chosen time/ date period | Software Development | 2.5 | Do we need to provide download option for report? If Yes what kind of format we need to display over there?
Module testing | Testing before milestone | Testing | 1.5
API | API Functionality
Registration API for EMPLOYEES | Registration process through Email and Password | Software Development | 0.375
Create Orders | Employees will be able to sell the products to the customers by creating orders. They will be able to choose between “in store” or “on call” orders when initiating an order | Software Development | 0.875 | What is On call here ?
| They will be able to create orders by entering the details such as Customer name, Product name, Product quantity, Offer, and Discount | Software Development | 0.625
| Employees will be able to select the customer by entering registered mobile number; if customer is not registered employees will be able to register the customer. Note: Orders can be cancelled before the bill/ receipt is generated. | Software Development | 1.5
Scan Products | Employees will also be able to view the current stock levels of the products. | Software Development | 0.375
Accept Payments | Update server DB for payment method chose by EMP | Software Development | 0.375
API for socket.io | Need to create API for socket process where Mobile and server can start process in real time | Software Development | 4
Manage Profile | Employees will be able to update the details like password, first name, last name, phone number, gender, birthdate, and profile photo” | Software Development | 0.75
View Order | There will only be 1 screen where customers will be able to view the placed orders and amount to be paid | Software Development | 0.375
| Customers will be able to fill the form with their basic information such as name, email ID, phone number, and date of birth. The information will not be mandatory and they will have an option to skip it. | Software Development | 0.5
User Acceptance Testing / Deployment / Revisions
Integration | integration with the live server | Software Development | 3
UAT Revisions with QA | QA Testing after live and solve issue | Software Development | 5
Go Live Deployment | provide all the details to client and confirmation of project | Software Development | 2
NOTE | We are assuming that client will provide Admin dashboard theme or we can suggest free best theme for admin